## Sheet1
No | Request Name | Status | Progress | Priority | Severity | Difficulty | PIC | Phase | Requestor | Delivered Date | Notes
1 | Penambahan folder Draft email | [6 empty] | Phase 2 | CC
2 | Penambahan feature Flag Email | [6 empty] | Phase 2 | CC
3 | Penambahan feature Recall Email | [6 empty] | Phase 2 | CC
4 | Penambahan feature related Email | [5 empty] | TBC | Phase 2 | CC
5 | Penambahan Template Signature | Done | 100% |  |  |  |  | Phase 1 | CC | Des 2021
6 | Penambahan pada Escalate TT bisa search by customer name, customer ID, End customer ID & End customer name | [6 empty] | Phase 2 | CC
7 | Penambahan folder sent item | Done | 100% |  |  |  |  | Phase 1 | CC | Des 2021
8 | Penambahan Address Book | [6 empty] | Phase 2 | CC
9 | Penambahan Foldering Rules Email | Done | 100% |  |  |  |  | Phase 1 | CC | Des 2021
10 | Penambahan informasi email yang di remark (Followup, High & Low Importance)) Level Message Set Importance (Send Email) | OnProgress |  | 1 |  |  |  | Phase 1 | CC
11 | Penambahan informasi email yang di remark (Followup, High & Low Importance)) Level Message Set Importance (Receive/list email) | OnProgress |  | 2 |  |  |  | Phase 1 | CC
12 | penambahan alert email yang belum di respons selama 5 menit dimana akan ada notifikasi (reminder) | [6 empty] | Phase 3 | CC
13 | Penambahan jumlah email yang masuk di setiap folder dan akan berkurang setelah email tersebut di respons | Done | 100% |  |  |  |  | Phase 1 | CC
14 | Penambahan status ON PROGRESS di field action sebagai penanda email tersebut sedang di kerjakan oleh tim custcare | [6 empty] | Phase 3 | CC
15 | Penambahan field user [by login] yang melakukan action | Done | 100% |  |  |  |  | Phase 1 | CC | Des 2021
16 | penambahan alert update berkala per 1 jam untuk customer LMS | [6 empty] | Phase 3 | CC
17 | Dashboard performance Agent | [6 empty] | Phase 3 | CC
18 | Penambahan Auto fill di kolom source | OnProgress |  | 3 |  |  |  | Phase 1 | CC |  | Catatan Feedback (Last UAT): 1. saat create TT source nya masih manual
19 | Penambahan value Subject, Email date, dan Body/Notes dari email masuk | OnProgress |  | 4 |  |  |  | Phase 1 | CC |  | Catatan Feedback (Last UAT): 2. saat create TT subject,date email dan body email masih manual
20 | Fitur Compose Email/Send New Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
21 | Fitur Reply/Reply All Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
22 | Fitur Forward Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
23 | Fitur List Folder Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
24 | Fitur UI List Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
25 | Fitur Filtering List Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021 | Enhance fitur 26 Januari 2022 (Last UAT) - Feedback : Mungkin filter Action By & Date received bisa diaktifkan agar pencarian lebih mudah
26 | Fitur Paging List Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021 | Enhance fitur 26 Januari 2022 (Last UAT) - Feedback : Pada saat dicoba filter from by cust Hypernet nampil total page/records : 34/335 namun jika ingin dilakukan lagi jumping ke next page dengan mengisi nomor page (sample page 5) maka halaman inbox akan kembali ke Inbox all bukan lagi dalam filtering From : Hypernet.
27 | Fitur Fetch Otomatis Rules Folder dari Outlook | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
28 | Fitur Notifikasi Email Masuk | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
29 | Fitur Tracking History Email/Agent | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
30 | Fitur Escalate Ticket By CRT | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
31 | Fitur Badge untuk menentukan banyaknya Email yang masih Unread di masing masing Folder | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
32 | Fitur Sync Update Email ke Server Outlook | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
33 | Fitur Crawling Email di Inbox | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
34 | Fitur Crawling Email di SubFolder Inbox | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
35 | Fitur Crawling Email di Child SubFolder Inbox | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
36 | Fitur Crawling Email di Sent Items | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
37 | Fitur Crawling Attachment Inline Body | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
38 | Fitur Crawling Attachment External Body | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
39 | Fitur Crawling Update Rules Folder | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
40 | Fitur Crawling Update Email | Done | 100% |  |  |  |  | Phase 1 |  | Des 2021
41 | Fitur Service Web Push Notifikasi | Done | 100% |  |  |  |  | Phase 1 |  |  | New Fitur 26 Januari 2022 (Last UAT)